## Slide 1: Sunshine Coast
Primary Care Social Worker

## Slide 3: PCN Social Worker Updates!
Interviews began this week (Feb 15th!)
Could start as early as mid-March

## Slide 4: Living Lab Framework
PDSA Objectives:
Develop a foundation of success for the SW. The Living Lab is meant to provide an environment where newly hired PCN staff get a first-hand view of primary care in action, provide an opportunity for FPs to learn about services the SW can provide their patient panel, and co-design processes to suit the Coast's rural needs. This model promotes relationship building amongst the team and shared accountability.
    Who: Clinics (FPs & staff), VCH (Manager & SW), Patients, Community Partners
    When: Living Lab 1.0 (1-2 months), Living Lab 2.0 (3-4 months)
    Where: in-clinics, Home Health, & virtual visits
    What: Co-design of tools and processes, testing limited referrals, expansion of pilot, and triple aim (patient, provider, and system) evaluation

## Slide 5: Living Lab 1.0: Phased Objectives
Orientation
Clinic Meet & Greets
Foundational Tools
Limited Referrals
Living Lab 1.0: co-design of tools between SW, Clinic, VCH & Division
Mid-March?

## Slide 6: Living Lab 1.0: Relationship Building
Orientation
Clinic Meet & Greets
VCH Orientation
    Main Desk: Home Health
    Equipment: laptop, cell phone,
    Accounts: Paris, Zoom
Training (Division & VCH)
    PCN & Living Lab Overview
    Living Lab 1.0 Deliverables
    SW Professional Practice Training
Clinic Meet & Greets
    Intros and Q&As
    Scheduled Clinic Tours & Training

## Slide 7: Living Lab 1.1: Co-Design of Tools
Referral Guide
Target Population refined for first SW (mild to moderate)
Access Form & Charting
Task template
Referral Process
Eligible patient
Integration into each clinic’s EMR
Reporting
Types of encounters (in-person, virtual, offsite)
Services provided
Limitations of Service (ie. short term?)
FP identifying patients
Patient scheduling & intake
Communication (ie. Referral accepted, care conferencing & discharge summary)
Charting Template
Foundational Tools (Plan)

## Slide 8: Living Lab 1.2: Limited Referrals
Who: 1-2 FPs per clinic, mild to moderate complexity patients
When: 2-4 weeks
What:
1-2 referrals per week per clinic (ie. 5-10 referrals for SW/week)
Identify problems or unexpected observations through check-ins
Summarize and reflect on learnings
Limited Referrals (Do/Study)

## Slide 9: Living Lab 2.0: Expansion
Who: Expand to FPs interest in participating in pilot
When: 3-4 months
What:
Test and revise processes & tools
Change management (eg. Team based care training)
Assess patient & provider satisfaction (surveys & focus groups)
Evaluation of SW capacity with refined target population & defined services
New PDSA Cycle

## Slide 10: SW Living Lab Objectives
Plan
Do
Study
Act
Living Lab 1.0 [1-2 months] relationship building, shared learning, co-design of tools, target population, service parameters/limitations
Living Lab 2.0 [3-4 months] stress test processes, refined target population and services limitations. Assess triple aim (patient, provider and system affects)

## Slide 11: The PCN Team Responsibilities
SW
Tools & Processes
Clinics
Space & EMR
Division
Coastal VCH
HR/Supervision
Space & Equipment
Finances
Project Management
Patient Referrals
Reporting
Clinic Engagement & Support
SW Training
Training
FP & Patient Education
Evaluate capacity (eg. admin, charting, encounters, TBC, system navigation, etc)
SW service delivery
Participating in evaluation
Change Management
Change Management

## Slide 12: What’s Missing? [breakout rooms]
Breakout groups: randomly assigned ( 2 x groups of 3-4)
Questions:
    What are your concerns with this approach?
    What do you think needs to be done before the SW begins?
    What can wait until after the SW starts working with clinics?

## Slide 13: Next Steps to Prepare
VCH
    Equipment
    Home Health Space
    Professional Practice Training
Clinics - Readiness
    Clinic interviews being scheduled
    FP champions being identified
    Space & capacity assessments
Division - Logistics
    Onboarding Schedule (post-consultation with VCH, clinics, and other partners)
    Overhead contributions to clinics (eg. EMR licenses)
    Clinic-VCH Agreements – a) Team charting , b) service agreements, c) invoicing?
    PSP Support
  PCN Steering Committee tomorrow – solicit input from Primary Care Providers, Community & Patient Perspective
  PSP & DoBC Team-based Care Education & Change Management (mid-April?)